## Risk template
RISK ANALYSIS TABLE for Decagon-CondoManagementSystem
Last Update: 03-02-2024
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
15 - High | Cross-platform vulnerabilities | Insuffiecient security measures. Weak password policies. | Lack of two-factor authentication | Unauthorized access to user profiles and sensitive data.Data leaks.Exploitation of the platform-specific vulnerabilities. | 3 | 5 | Implement two-factor authentication. Enforce strong password policies. | Form a security team for continuous monitoring and response. | 8 - Medium
16 - High | Complex User Interface | Lack of user testing or feedback. Inadequate UI design and navigation. | Limited resources for UX/UI design. Tight project deadlines leading to rushed UI development. | Decreased user satisfaction and adoption. | 4 | 4 | Prioritize UX/UI testing and iteration. Accept that some level of complexity may exist but aim to minimize it through user feedback and iterative design improvements. | Invest in UX/UI expertise, conduct user testing, simplify navigation, and prioritize user feedback throughout development. | 5 - Low
8 - Medium | Inadequate test cases for functional validation | Lack of some end to end test cases. Lack of component tests. Lack of integration tests. | Limited availability of testing resources. Lack of testing knowledge among the team. | Increase the chances of arising problems later-on in the development process | 2 | 4 | Prioritize critical test cases and increase coverage over time. | Implement automated testing to ensure coverage. Conduct review sessions and update the test cases as needed. | 4 - Low
12 - High | Expertise and Knowledge Requirements | Dependency on individual team members with specialized knowledge. Insufficient training or documentation. | Rapidly evolving technology landscape. Limited budget for training or hiring. | Potential delays in development. | 3 | 5 | Accept that some learning curve is inevitable, but aim to mitigate delays by providing training opportunities and documentation. | Invest in training for team members, encourage knowledge sharing, and consider hiring experts or consultants for critical areas. | 9 - Medium
9 - Medium | Changes in requirements during development | Lack of clear communication channels. Unclear or ambiguous requirements documentation. | Complex Project scope. | Delays and work overload. | 3 | 5 | Accept that some degree of miscommunication is inevitable, but aim to mitigate its impact through regular communication and clarifications | Establish clear communication channels, document requirements thoroughly, and involve stakeholders in regular reviews and feedback sessions. | 6 - Low
CONFIDENTIAL